## Sheet1
Bug # | Reported Date | Reported By | Priority | Status | Owner | Description | Expected Results | Actual Results | Milestone | Steps to Reproduce
1 | 2024-10-11 | Andie | P4 | In progress | Avi Sharma | Sounds for picking up keys or dying is not being played if the wall collision is play at the same time | The key pick up sound or dying sound should play | You should be able to play multiple sound effects on top of another | Milestone 1 | If the key is near an obstacle (trees/stones), press the WASD key accordingly to move into the wall and press the E key to pick up the key or wait for robot to collide with the player.
2 | 2024-10-12 | Andie | P0 | Completed | Avi Sharma | Collision with trees on top results in an error | Collision with tress on top should play a sound | Collision with trees on top results in an error | Milestone 1
3 | 2024-10-12 | Andie/Avi | P4 | Completed | Song Shi | BFS does not work if the player is in line with the robot (when an object is in line and in between the robot and player) | The robot moves towards the player | The robot gets stuck at the obstacles | Milestone 1
4 | 2024-10-12 | Zeen | P5 | Not started | Zeen Lin | Visual effects could be improved to be more realistic when the player moves to the tree tiles | The tree leaves visually cover some parts of the player's body | The tree leaves are not visually covering the player body when the player stands on the tree tiles | Milestone 1
5 | 2024-10-29 | Andie | P1 | Completed | Avi Sharma | Keys spawning in walls not accessible by players | Keys spawning outside walls and accessible by players | Random spawning of keys made the keys not accessible by players. | Milestone 2 | set spawn locations
6 | 2024-10-29 | Andie | P0 | Completed | Avi Sharma | Robots spawning in walls and not able to move out | Robots to spawn outside the walls and move around | Random spawning makes robot spawn inside the walls and not be able to move | Milestone 2 | set spawn locations
7 | 2024-10-29 | Andie | P1 | Completed | Avi Sharma | Player walking animation stops even if the player is still walking | Player should keep walking animation when walking | Player only does first 2 frames of walking animation when WASD is initially pressed. | Milestone 2 | fix logic for animation
8 | 2024-10-30 | Avi | P2 | Completed | Andie Lizo | Player health bar - current health gets set to 0 when - key is pressed | Current health value should decrease by 10 | Current health value gets set to 0 | Milestone 2 | change from int to float
9 | 2024-10-30 | Avi | P2 | Completed | Avi Sharma | When player is walking - then attacking is not possible | Player should be able to attack (go through attack animation) | Player keeps walking | Milestone 2 | fix logic for animation
10 | 2024-10-31 | Avi | P1 | Completed | Andie Lizo | Player Inventory is erased when moving to another level | Inventory contents should remain the same thoughout levels (unless the player dies) | Inventory contents go away after moving to next level | Milestone 2 | keep inventory in registry when loading new level
11 | 2024-11-03 | Avi | P4 | Not started | Song | Player attacking up instantly kills the robot | Player attacking the robot in the updward direction should damage the robot but not kill it | Robot dies in one shot | Milestone 2 | Move under the robot and then press W key to look up and left click to attack
12 | 2024-11-03 | Avi | P2 | Completed | Song | Projectile hiting the walls sometimes creates a new wall (very infrequently) | Projectile should just hit the wall | Projectile htting the wall sometimes adds a new wall | Milestone 2 | Not consistent - Moving towards the end and killing the robots and moving back and dodging projectiles created the new wall after impact with the wall.
13 | 2024-11-15 | Andie | P3 | Completed | Andie Lizo | Sprint doesn't work right away (player needs to change direction for it to work) | The player should sprint in the regular direction | The player walks in the direction even though shift key is pressed | Milestone 3
14 | 2024-11-16 | Avi | P3 | Completed | Song | If player is moving in a direction and the quits the game, the loading game state will continue the movement even if no key is pressed | Player should not be movinig | Player keeps moving even though no keys are pressed | Milestone 3
15 | 2024-11-20 | Andie | P4 | Completed | Avi Sharma | Stamina should restart as well on death | Restarting after dying makes the stamina stay as it was before | Stamina should be back to 100 | Milestone 3
16 | 2024-11-20 | Andie | P3 | Completed | Ashish | Sprint keeps going on even when stamina is below 0 | Sprint should stop when stamina is below 0 | Sprint keeps going on even when when stamina is below 0 | Milestone 3
17 | 2024-11-20 | Avi | P3 | Completed | Andie | Teleporter through wall edges allow player to go to next level | The player should not be able to teleport through to a next level | The player can teleport through to the next level. | Milestone 3 | For the bottom wall of Level 2, use the Teleporter to make to the boss level
18 | 2024-11-20 | Andie | P1 | Completed | Zeen | Pressing Keys before start screen causes to crash | Game should not crash | Game crashes | Milestone 3
19 | 2024-11-20 | Avi | P3 | Completed | Andie | Robot dies during capture UI screen | Robot should no die | Robot sometimes dies if there is a delayed projectile causing the UI screen to disappear | Milestone 3
20 | 2024-11-20 | Avi | P5 | Completed | Andie | The inventory 1-3 slots gets shuffled by 1 if the armor plate is in 1-3 slots and upgraded | The 1-3 slots should work normally for the item | The 1-3 slots are offset by 1 due to the amor plate in 1-3 slots | Milestone 3
21 | 2024-11-23 | Ashish | P1 | Completed | Andie | If we try to dissemble the robot, the game freezes when trying to move or any other key press | The game should continue as it is | When we dissemble the robot instead of capturing it, it freezes the game | Milestone 4
22 | 2024-11-24 | Avi | P3 | Completed | Andie | Capturable robot show health as full after dying during the capture UI screen | The enemy robot should die and have the health as 0 during the capture UI screen | The enemy robot health goes to full after dying during the capture UI screen | Milestone 4
23 | 2025-11-25 | Andie | P1 | Completed | Song | Game crashes when loaded for the first time. Also when you restart the game and start it again | Game should start a new save or load from an existing one depending on user input | game crashes when loaded for the first time | Milestone 4
24 | 2025-11-26 | Zeen | P0 | Completed | Andie Lizo | Game crashes when picked up item or disassembled robot that gain item, which is occupied the third slot (found on commit id 7068a1ef) | Game should not crash | Game crashes | Milestone 4
25 | 2025-11-27 | Zeen | P2 | Completed | Andie Lizo | The picked-up armor plate can increase the Armor status without being consumed during use | The picked-up armor plate increases the Armor status when used and is consumed in the process | Players can use the armor plate to infinitely increase their Armor status without consuming armor plate | Milestone 4
26 | 2024-11-28 | Song | P1 | Completed | Andie Lizo | player lose control when moving close to potion in tutorial level(Potion in level 1 won't cause this) | Player should able to have control on it's character | Player loses control | Milestone 4 | Walk to potion in the tutorial level
27 | 2024-12-01 | Avi | P1 | Completed | Andie | Player doesn't die from radiation | When player health goes to 0 from radiation and no collision then it should die | Player does not die | Milestone 4
28 | 2024-12-02 | Avi/Andie | P1 | Completed | Andie | When you die, and you don't use the armor, you can go outside the range of the tutorial room | Player should not be able to go outside the tutorial room | Player is able to move outside after using the keycard while being in the tutorial state | Milestone 4